## RABILL-01 (hidden)
THE LAWRENCE SCHOOL , LOVEDALE
WORK DONE STATEMENT
Name of Work :Dismantling & re – fabrication of temporary stables & Engineering stores
S. No | Category | Description of work | Unit | Nos | L | B | D | Quantity | Rate | Amount
A | Temporary Stables
1 | Demolition | Demolition of Concrete in ground floors and paving’s not exceeding 15 cm thickness (below or above ground level) | Cum
|  | Partition 1-4 |  | 1 | 13.3 | 4.4 | 0.05 | 2.926
|  | M/LS/EM/AWT/505 | [5 empty] | 2.926 | 761 | 2226.686
2 | Refabrication | Labour charges towards re fabrication of GI Sheet covering for butteress provision over Wet land no:2.Note:Necessary items like GI Sheets,GI Pipes,MS Angles are available at site.Necessary fixtures like j Bolt,Bolt/Nuts/Screws,welding rods etc is under vendors scope | Sft | [7 empty] | Demolition of Concrete in ground floors and paving’s not exceeding 15 cm thickness (below or above ground level)
|  | Partition outer |  | 1 | 13.3 | 3.12 | 10.76 | 446.497
|  | Internal partition Avg.Ht |  | 3 | 4.4 | 3.4 | 10.76 | 482.9088
[8 empty] | 929.4058 | 31.36 | 29146.1646
3 | PCC 1:4:8 | Material and Labour for laying PCC 1:4:8 | Cum
|  | Partition 1-4 |  | 1 | 13.3 | 4.4 | 0.1 | 5.852
[8 empty] | 5.852 | 4659.43 | 27266.9844
3 | Painting | Material and Labour for applying synthetic enamel paint of one coat over the GI sheet with primer for uniform and smooth surfaces, all as specified and as directed. | Sqm
|  | Partition outer |  | 2 | 13.3 | 3.12 |  | 82.992
|  | Internal partition Avg.Ht |  | 6 | 4.4 | 3.4 |  | 89.76
|  | M/LS/EM/AWT/505 | [5 empty] | 172.752 | 81 | 13992.912
4 | Internal Painting | Material and Labour for One coats of oil bound distemper in all walls, over a coat of primer all as specified and as directed. Including preparation of old plastered surfaces. | Sqm
|  | Partition1-4 |  | 1 | 13.3 | 2.9 |  | 38.57
|  | wall |  | 2 | 4.4 | 3.4 |  | 29.92
[8 empty] | 68.49 | 81 | 5547.69
5 | weld mesh | Removing and fixing of M.S. grills made out of welded mesh 2"x 2"X 10 Gauge thick including fabrication such as cutting, bending, drilling for the required holes etc and complete.(WO No :M/LS/EM/RSQ/371 - 001 Date: 17/05/2016) | Sqm
|  | Partition-1-4 |  | 1 | 13.3 | 0.5 |  | 6.65
|  | Deduction wall |  | -3 | 0.5 | 0.5 |  | -0.75
[8 empty] | 5.9 | 186.22 | 1098.698
|  | Total | [7 empty] | 79279.135

## TENDER
THE LAWRENCE SCHOOL , LOVEDALE
TENDER SCHEDULE
Name of Work : Repair / replacement of rainwater gutter and providing cement coving on edges at senior school building.
Note: This work has to be executed at an height of 16 m from GL, necessary ladder /scaffolding is under the scope of the contractor. Hence the contractor is requested to inspect the site before submitting the offer
S. No | Category | Description | Qty | Unit | Rate | Amount | Remarks
1 | Removal of existing cement coving on roof edges | Demolition / dismantling of Concrete/cement coving on roof top not exceeding 15 cm thickness | 9.9 | Cum
2 | Clearing debris | Clearing the debris generated out of sl.no. 1 at roof top - the demolished concrete/brick, etc., to be transported from the site and deposited as directed by the Engineer-in-Charge. Note: Transporting distance not more than 2 KM | 9.9 | Cum
3 | PCC 1:2:4 Cement coving on roof edges mixed with SBR chemical for bonding | Material & Labour for Cement concrete type B-0, 1:2:4 (12/6 mm graded aggregate) in coving, coping, etc., including finishing the surfaces even & smooth with using extra cement mixed with SBR chemical for bonding and pigments of approved quality & required form work etc., Cement Grade - PPC 53 Cement Make - ACC / ULTRATECH / CORAMANDAL / CHETTINAD / DALMIA / SANKAR/RAMCO | 9.9 | Cum
4 | Plastering | Material and labour for plastering with cement mortar 1:5 to 12 mm thick in brick walls etc and finishing the surfaces even and fair without using extra cement and SBR chemical for bonding, including curing, finishing etc, and complete. Cement Grade - PPC 53 Make - ACC / ULTRATECH / CORAMANDAL / CHETTINAD / DALMIA / SANKAR | 55 | Sqm
5 | Structural Steel "L" Angle support for rainwater gutters | Supply & erection using SHS Section, edges of the tubes shall be welded with MS Plate etc. Roof trusses (framed), trussed purlins crane gantries, rails and fastenings and heavy bracket framing (Beam, tee, angle channel or flat sections) including distance pieces, cleats etc. | 500 | Kgs
6 | External Apex painting for cement coving on top edges | Material and Labour for two coats of Apex exterior paint over a coat of primer on newly plastered surfaces, including preparation surfaces, etc., in all walls all as specified and as directed including preparation of new surfaces, including necessary scaffolding etc., Make - Asian paint | 55 | Sqm
7 | Enamel Paint for the steel support of rain water gutter | Material and labour for painting two coat of synthetic enamel paint in Wooden/metal surfaces including preparation of old surfaces etc., Make - Asian paint | 100 | Sqm
8 | Rain water gutter | Material and labour for fixing of rain water gutter made out of 0.5 mm thick galvalume color coated plain sheet with necessary MS 'L' angle including painting of MS items, etc., Gutter Size: pls refer the drawing in the remarks column (6"+8") x 7" x (8"+1") with support of MS 'L' angle (25*25*5mm) support at every 1 meter interval. Note: 1. Necessary scaffolding for fixing the gutter ht.15m from ground to be included in the rate 2. Necessary silicon/ M seal to be provided in the joints of the gutter sheet all sides to ensure to water leakage in the joints. Sheet Make - JSW / BHUSHAN | 40 | Rmt
9 | Labour for realignment of rainwater gutter at 18 Mtrs height | Labour only for aligning the existing rainwater gutter to ensure necessary gradient/slope is properly maintained for free flow of rain water. If necessary additional MS support to be provided as instructed by Engineer In-charge. (Charges for additional MS support shall be paid under separate item) Note: 1. Necessary ladder arrangement is under the scope of the contractor for the height of 20m. 2. Necessary silicon/m seal to be provided in the joints of the gutter sheet all sides to ensure to water leakage in the joints | 225 | Rmt
11 | Plain Galvalume sheet | Supply and fixing of plain GalvaIume sheet of 0.47 mm thick TCT 300 Mpa 150 GSM colour coated sheets with polyester coating of approved colour on the top over the 5 microns primer & 5 microns back up epoxy coating at the bottom & fixing with necessary screws etc all as specified by the Engineer in charge. Note: Colour of the sheet to be approved by the school authorities.Sheet make - JSW / BHUSHAN | 50 | Sqm
12 | Box type rainwater down take pipe made out of plain galvalume sheet | Material and Labour for providing rain water down take box duct made out of colour coated plain GalvaIume sheet of 0.47 mm thick TCT 300 Mpa 150 GSM of size 170mm*100mm made as box type including cutting, bending and fixing with necessary clamps to the wall. Silicon/ M seal to be applied on joints to ensure there is no leakage an all as directed by the Engineer-in-charge Note: Colour of the sheet to be approved by the school authorities. Sheet make - JSW / BHUSHAN | 100 | Rmt
13 | L- profile Flashing | Supplying and fixing of corner L-flashing of 150 mm 'L' profile on 0.47mm thick colour coated plain galvalume sheet with necessary screws on either side all as directed by engineer in charge. | 50 | Rmt
14 | 9" thick wire cut brick work using M sand | Providing wirecut Brick works, in cement mortar 1:4 (1 cement : 6 M sand) ,Wire Cut Bricks are machine made. The edges are sharp and borders are straight Size – 9"x 3"x 4.5" smooth surface finish Compression Strength should not be less than 105 kg/sq cm Water absorption should not exceed 20%, the rate including Polyurethene pointing ,cost and conveyance of all materials to site, hire and labour charges for scaffolding, watering, curing, raking of joints etc. complete as directed by engineer incharge. | 1 | Cum
TOTAL
GST @ 18%
GRAND TOTAL
Signature of the Contractor